## RoC
RECORDS OF CHANGES
# | Date | In Charge | Change Notes
1
2
3
4
5
6
7

## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | LOC | Function/Screen Details | Planned | In Charge | Status
0 | User Login | Common | Simple | 60 | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | Iteration 1 | kinhhghe153111 | Done
1 | User Register | Common | Simple | 60 | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | Iteration 1 | thanhnthe150825 | Done
2 | Reset Password | Common | Medium | 120 | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | Iteration 1 | anhntlhe150434 | Done
3 | User Authorization | Common | Complex | 240 | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | Iteration 1 | kinhhghe153111 | Done
4 | User Profile | Common | Simple | 60 | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | Iteration 1 | congnxhe151350 | Done
5 | Change Password | Common | Simple | 60 | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Iteration 1 | congnxhe151350 | Done
6 | Home | Public | Medium | 120 | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | Iteration 3 | hieunnhe153057 | Done
7 | Blogs List | Public | Simple | 60 | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | Iteration 2 | congnxhe151350 | Done
8 | Blog Details | Public | Simple | 60 | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | Iteration 2 | thanhnthe150825 | Done
9 | Courses List | Public | Complex | 240 | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | Iteration 3 | anhntlhe150434 | Done
10 | Course Details | Public | Medium | 120 | Show subject details (including title, tag line, brief info, lowest price package option (original price, sale price), product description, and a Register button) + the sider with the subject search box, subject categories, featured subjects, static contacts/links | Iteration 3 | thanhnthe150825 | Done
11 | Course Register | Public | Medium | 120 | This is a pop-up screen which allow the user to register for access a subject. On this screen, the user needs to choose appropriate subject price package & input his/her information (full name, email, mobile, gender); A logged in user doesn't have to input those contact information | Iteration 3 | congnxhe151350 | Done
12 | My Registrations | Customer | Simple | 60 | Show the list of user's registration + the sider with the subject search box, subject categories, static contacts/links - Each registration includes below information: id, subject, registration time, package, total cost, status, valid from, valid to; - If the registration is still in the submitted status, the users can choose to cancel it or comming back to the Course Register pop-up to edit it) | Iteration 3 | congnxhe151350 | Done
13 | My Courses | Customer | Simple | 60 | for the customer to view his/her access-allowed courses | Iteration 3 | hieunnhe153057 | Done
14 | Lesson View | Customer | Complex | 240 | allow customer to access the course lessons for his/her studying | Iteration 4 | kinhhghe153111 | Done
15 | Quiz Lesson | Customer | Medium | 120 | This allows the user to take the topic quiz or view the quiz results | Iteration 4 | anhntlhe150434 | Done
16 | Quiz Handle | Learning | Complex | 240 | This screen allows the user to browse and answer the quiz questions | Iteration 4 | anhntlhe150434 | Done
17 | Quiz Review | Learning | Complex | 240 | This screen allows the user to review the details of the quiz that s/he has just taken | Iteration 4 | congnxhe151350 | Done
18 | Dashboard | Marketing | Complex | 240 | Show statistics of new subjects (new, all), new registrations (success, cancelled, submitted), revenues (total, by subject categories), customers (newly registered, newly bought), and the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | Iteration 4 | thanhnthe150825 | Done
19 | Post Details | Marketing | Medium | 120 | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | Iteration 1 | hieunnhe153057 | Done
20 | Post List | Marketing | Medium | 120 | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status; also the user can search the post by title - The list can be sortable by title, category, author, featured, or status - The page also have the button/link that allows the user to add new or choose to view/update/show/hide an existing post | Iteration 1 | kinhhghe153111 | Done
21 | Sliders List | Marketing | Simple | 60 | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | Iteration 1 | anhntlhe150434 | Done
22 | Slider Details | Marketing | Simple | 60 | Show detailed slider information (image, title, backlink, status, notes) | Iteration 1 | congnxhe151350 | Done
23 | Subjects List | Course Content | Medium | 120 | Show the list of course paginatedly. The shown information for each subject include the id, name, category, number of lessons, owner, and status The user can: - Filter the list by course category & status - Search the course by the name - Choose to add new course (redirect the user to the New Subject page for that) - Edit course information (linked to the Subject Details for that) | Iteration 2 | anhntlhe150434 | Done
24 | New Subject | Course Content | Medium | 120 | The screen is shown with below information for the user to input new course information: name, thumbnail image, category, featured flag, owner, status, and description | Iteration 2 | anhntlhe150434 | Done
25 | Subject Details | Course Content | Complex | 240 | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. Only the admin can change the status to Published or Unpublished + add/edit the price packages | Iteration 2 | kinhhghe153111 | Done
26 | Subject Dimension | Course Content | Simple | 60 | This page allow the admin/expert to input or edit subject dimension information, including the following detailed information: type, name, description | Iteration 2 | thanhnthe150825 | Done
27 | Price Package | Course Content | Simple | 60 | This page allows the admin to input or edit subject price package information, including the following detailed information: name, access duration (in months), status (read-only), list price, sale price, description. The expert can only view the information. | Iteration 2 | thanhnthe150825 | Done
28 | Subject Lessons | Course Content | Medium | 120 | This page shows the list of lessons for a selected package. On this page, the admin/expert is allowed to activate/deactivate, or call the Lesson Details for adding new or editing existing lesson | Iteration 3 | thanhnthe150825 | Done
29 | Lesson Details | Course Content | Medium | 120 | This page allows the admin/expert to input/edit the lesson information | Iteration 3 | kinhhghe153111 | Done
30 | Questions List | Test Content | Medium | 120 | The existing questions list for a specific subject/course are shown here (paginatedly). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information are shown for each quesiton in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | Iteration 2 | congnxhe151350 | Done
31 | Question Details | Test Content | Complex | 240 | This page allows the admin/expert to input or edit questions information, including following information: subject, dimension(s), lesson, status, content, media (image, audio, video – with preview option), answer options (with the key marked + ability to add, edit, delete), and explanation | Iteration 2 | kinhhghe153111 | Done
32 | Question Import | Test Content | Medium | 120 | This is a pop-up screen which allows user to choose import file and then import the questions in the file into the questions bank. The screen also provides the option for the user to download the sample import template. | Iteration 3 | kinhhghe153111 | Done
33 | Quizzes List | Test Content | Medium | 120 | The existing quizzes are showned in this page paginatedly: - The user can filter the list by subject, quiz types + search quizzes by the name - Each quiz includes following information: id, name, subject, level, # question, duration, pass rate, and the quiz type. From this page, the user has the options to call to the Quiz Details page for adding new or editing existing quiz + delete the quiz. Please note that the quiz can be editted only when there is not any test taken yet. | Iteration 2 | hieunnhe153057 | Done
34 | Quiz Details | Test Content | Medium | 120 | This page allows the user to input or edit quiz information | Iteration 3 | kinhhghe153111 | Done
35 | Registrations List | Sale | Medium | 120 | Show the list of users' registrations - Each registration includes below information: id, email, registration time, subject, package, total cost, status, valid from, valid to, last updated by; - The user can filter the list by subject (searchable), registration time (from, to), status + can search by the email - The list can be sorted by id, email, registration time, subject, package, total cost, status, valid from, valid to - From the list, the user can choose to add new or edit an existing registration via the Registration Details screen as below | Iteration 4 | hieunnhe153057 | Done
36 | Registration Details | Sale | Medium | 120 | Show detailed registration information (subject, package with list price/sale price, full name, gender, email, mobile), registration time, sale, status, valid from, valid to, notes) from that for the user to add new or change the status of a registration with relevant notes (if a registration is created by the user, then s/he can edit other registration information). On changing a registration status to Paid, if the user with relevant registered email does not exist, the system would create one and send back to the user the login information (link, email, pass) along with the other notification notes | Iteration 4 | hieunnhe153057 | Done
37 | Users List | Admin | Simple | 60 | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | Iteration 1 | hieunnhe153057 | Done
38 | User Details | Admin | Simple | 60 | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | Iteration 2 | hieunnhe153057 | Done
39 | Settings List | Admin | Simple | 60 | Show the paginated list of settings (include settings' id, type, value, order, status): - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Iteration 1 | thanhnthe150825 | Done
40 | Setting Details | Admin | Simple | 60 | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | Iteration 1 | thanhnthe150825 | Done

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | kinhhghe153111 | Done
2 | User Register | Common | Simple | 60 | thanhnthe150825 | Done
3 | Reset Password | Common | Medium | 120 | anhntlhe150434 | Done
4 | User Authorization | Common | Complex | 240 | kinhhghe153111 | Done
5 | User Profile | Common | Simple | 60 | congnxhe151350 | Done
6 | Change Password | Common | Simple | 60 | congnxhe151350 | Done
7 | Post Details | Marketing | Medium | 120 | hieunnhe153057 | Done
8 | Sliders List | Marketing | Simple | 60 | anhntlhe150434 | Done
9 | Slider Details | Marketing | Simple | 60 | congnxhe151350 | Done
10 | Users List | Admin | Simple | 60 | hieunnhe153057 | Done
12 | Settings List | Admin | Simple | 60 | thanhnthe150825 | Done
12 | Setting Details | Admin | Simple | 60 | thanhnthe150825 | Done
13 | Post List | Admin | Medium | 120 | kinhhghe153111 | Done

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Subjects List | Course Content | Medium | 120 | anhntlhe150434 | Done
2 | New Subject | Course Content | Medium | 120 | anhntlhe150434 | Done
3 | Subject Details | Course Content | Complex | 240 | kinhhghe153111 | Done
4 | Subject Dimension | Course Content | Simple | 60 | thanhnthe150825 | Done
5 | Price Package | Course Content | Simple | 60 | thanhnthe150825 | Done
6 | Questions List | Test Content | Medium | 120 | congnxhe151350 | Done
7 | Question Details | Test Content | Complex | 240 | kinhhghe153111 | Done
8 | Blogs List | Public | Simple | 60 | congnxhe151350 | Done
9 | User Details | Admin | Simple | 60 | hieunnhe153057 | Done
10 | Quizzes List | Test Content | Medium | 120 | hieunnhe153057 | Done
11 | Blog Details | Public | Simple | 60 | thanhnthe150825 | Done

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Courses List | Public | Complex | 240 | anhntlhe150434 | Done
2 | Course Details | Public | Medium | 120 | thanhnthe150825 | Done
3 | Course Register | Public | Medium | 120 | congnxhe151350 | Done
4 | My Registrations | Customer | Simple | 60 | congnxhe151350 | Done
5 | Subject Lessons | Course Content | Medium | 120 | thanhnthe150825 | Done
6 | Lesson Details | Course Content | Medium | 120 | kinhhghe153111 | Done
7 | Quiz Details | Test Content | Medium | 120 | kinhhghe153111 | Done
8 | Home | Public | Medium | 120 | hieunnhe153057 | Done
9 | Question Import | Test Content | Medium | 120 | kinhhghe153111 | Done
10 | My Courses | Customer | Simple | 60 | hieunnhe153057 | Done

## Iteration 4
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 4 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Lesson View | Customer | Complex | 240 | anhntlhe150434 | Done
2 | Quiz Lesson | Customer | Medium | 120 | congnxhe151350 | Done
3 | Quiz Handle | Learning | Complex | 240 | kinhhghe153111 | Done
4 | Quiz Review | Learning | Complex | 240 | thanhnthe150825 | Done
5 | Dashboard | Marketing | Complex | 240 | hieunnhe153057 | Done
6 | Registrations List | Sale | Medium | 120 | congnxhe151350 | Done
7 | Registration Details | Sale | Medium | 120 | hieunnhe153057 | Done